## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a user, I want to upload knowledge-base documents so that I can query their content. | Must | Document extraction pipeline | Team | Completed
Sprint 1 | Sprint 1 | US-02 | As a user, I want documents in supported formats to be extracted and normalized for retrieval. | Must | Document upload | Prathiksha Gajula | Completed
Sprint 1 | Sprint 1 | US-03 | As a user, I want document text split into meaningful chunks so retrieval can find relevant context. | Must | Extraction/cleaning | Team | Completed
Sprint 1 | Sprint 1 | US-04 | As a user, I want semantic embeddings stored in a vector database for knowledge retrieval. | Must | Chunking | Team | Completed
Sprint 1 | Sprint 1 | H-US-01 | As a user, I want document chunks converted into reliable vector embeddings so knowledge can be searched semantically. | Must | Embedding | Team | Completed
Sprint 2 | Sprint 2 | US-05 | As a user, I want my question understood before retrieval so relevant knowledge is searched. | Must | RAG pipeline | Team | Completed
Sprint 2 | Sprint 2 | US-06 | As a user, I want queries routed appropriately between retrieval, clarification and direct response paths. | Must | Query understanding | Team | Completed
Sprint 2 | Sprint 2 | US-07 | As a user, I want retrieved chunks reranked so the most relevant evidence is used. | Must | Reranker | Team | Completed
Sprint 2 | Sprint 2 | US-08 | As a user, I want answers grounded in uploaded documents with source information. | Must | Response generation | Team | Completed
Sprint 2 | Sprint 2 | H-US-02 | As a user, I want retrieved chunks ranked using semantic, keyword and exact-match signals so the most relevant evidence is selected. | Must | Vector retrieval | Team | Completed
Sprint 2 | Sprint 2 | H-US-03 | As a user, I want low-relevance and duplicate chunks filtered and the best context assembled before answer generation. | Must | Candidate retrieval | Team | Completed
Sprint 3 | Sprint 3 | US-09 | As a user, I want follow-up questions to retain conversation context. | Must | Conversation ID/memory | Team | Completed
Sprint 3 | Sprint 3 | US-10 | As a user, I want clarification questions when my query is ambiguous or incomplete. | Must | Query understanding | Prathiksha Gajula | Completed
Sprint 3 | Sprint 3 | US-11 | As a user, I want voice input and spoken responses for easier interaction. | Should | Browser Speech APIs | Team | Completed
Sprint 3 | Sprint 3 | US-12 | As a user, I want to inspect sources, chunks, relevance and citations behind an answer. | Must | Retrieval metadata | Prathiksha Gajula | Completed
Sprint 3 | Sprint 3 | H-US-04 | As a user, I want follow-up queries to retain conversation state and be routed correctly between retrieval and clarification paths. | Must | Conversation state | Team | Completed
Sprint 3 | Sprint 3 | H-US-05 | As a system, I want agent outputs validated so multi-agent workflow state remains consistent during clarification and retrieval. | Must | Agent state and routing | Team | Completed
Sprint 4 | Sprint 4 | US-13 | As a user, I want to view query history and conversation statistics. | Should | Conversation API | Team | Completed
Sprint 4 | Sprint 4 | US-14 | As a user, I want charts for query activity, conversation usage and confidence distribution. | Should | History dashboard | Prathiksha Gajula | Completed
Sprint 4 | Sprint 4 | US-15 | As an administrator, I want analytics and knowledge-gap information to understand unanswered or low-confidence queries. | Should | Analytics service | Prathiksha Gajula | Completed
Sprint 4 | Sprint 4 | H-US-06 | As an analyst, I want semantically related user queries grouped into common themes so analytics and knowledge-gap detection can identify recurring needs. | Should | Query analytics | Team | Completed

## Sprint Backlog
Sprint | US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Estimated Effort (Hours) | Actual Effort (Hours)
Sprint 1 | PG-US-01 | PG-T01 | Designed document-upload interface and processing-status UI | TBD | TBD | Prathiksha Gajula | UI/UX | Completed (user-confirmed) | 4 | Not recorded
Sprint 1 | PG-US-01 | PG-T02 | Connected upload UI to backend and handled loading states and upload errors | TBD | TBD | Prathiksha Gajula | Frontend | Completed (user-confirmed) | 6 | Not recorded
Sprint 2 | PG-US-02 | PG-T03 | Build query/chat response layout and message states | TBD | TBD | Prathiksha Gajula | Frontend | Verify | 6 | Not recorded
Sprint 2 | PG-US-02 | PG-T04 | Connect query UI to retrieval response and source metadata | TBD | TBD | Prathiksha Gajula | Integration | Verify | 6 | Not recorded
Sprint 3 | PG-US-03 | PG-T05 | Implement CitationDisplay with inline numbered source citations | TBD | TBD | Prathiksha Gajula | Frontend | Implemented (reported) | 6 | Not recorded
Sprint 3 | PG-US-04 | PG-T06 | Build grounding evidence panel for retrieved chunks and citations | TBD | TBD | Prathiksha Gajula | Frontend | Implemented (reported) | 6 | Not recorded
Sprint 3 | PG-US-04 | PG-T07 | Display relevance scores and confidence with safe fallbacks | TBD | TBD | Prathiksha Gajula | Frontend | Implemented (reported) | 5 | Not recorded
Sprint 3 | PG-US-03 | PG-T08 | Check citation-to-source mapping and missing evidence UI | TBD | TBD | Prathiksha Gajula | Testing | Verify | 4 | Not recorded
Sprint 4 | PG-US-05 | PG-T09 | Build Analytics Dashboard page and responsive metric cards | TBD | TBD | Prathiksha Gajula | Frontend | Work reported; verify | 6 | Not recorded
Sprint 4 | PG-US-05 | PG-T10 | Add query activity charts, statistics and date filters | TBD | TBD | Prathiksha Gajula | Frontend | Work reported; verify | 8 | Not recorded
Sprint 4 | PG-US-06 | PG-T11 | Create Knowledge Gap summaries and topic visualizations | TBD | TBD | Prathiksha Gajula | Frontend | Work reported; verify | 7 | Not recorded
Sprint 4 | PG-US-06 | PG-T12 | Build gap detail view, search, severity filter and pagination | TBD | TBD | Prathiksha Gajula | Frontend | Work reported; verify | 8 | Not recorded
Sprint 4 | PG-US-05 | PG-T13 | Integrate analytics and gap APIs with loading/error/empty states | TBD | TBD | Prathiksha Gajula | Integration | Work reported; verify | 8 | Not recorded
Sprint 4 | PG-US-06 | PG-T14 | Test responsive views and dashboard/gap data handling | TBD | TBD | Prathiksha Gajula | Testing | Verify | 5 | Not recorded

## Stand up Meeting
Sprint | Day | Impediments / Risks | Action Taken / Next Step
Sprint 1 | TBD | Upload progress, backend connection and error feedback required attention. | Completed upload UI, backend connection and loading/error handling (user-confirmed).
Sprint 2 | TBD | Chat response may not expose sources clearly. | Verify response layout and retrieval metadata integration.
Sprint 3 | TBD | Inline citation numbers may not match displayed evidence. | Check CitationDisplay against chunk IDs and source mapping.
Sprint 3 | TBD | Missing scores or confidence may break the evidence panel. | Add or verify safe fallbacks for missing metadata.
Sprint 4 | TBD | Analytics API may return empty or partial data. | Verify loading, error and empty states.
Sprint 4 | TBD | Knowledge gaps may be hard to explore in large datasets. | Verify search, filters, severity and pagination.

## Retrospection
Sprint | Team Member | Start Doing | Stop Doing | Continue Doing | Action / Follow-up
Sprint 1 | Prathiksha Gajula | Check upload errors and loading states early | Leaving error handling until late | Clear upload progress and backend integration | Milestone 1 completed (user-confirmed); test evidence not supplied
Sprint 2 | Prathiksha Gajula | Check source metadata with UI | Showing unsupported source details | Readable chat responses | Verify API mapping
Sprint 3 | Prathiksha Gajula | Test citation mappings and missing scores | Assuming every response has full metadata | Evidence transparency | Review CitationDisplay and grounding panel
Sprint 4 | Prathiksha Gajula | Test empty data and filters | Assuming dashboard APIs always return data | Responsive dashboard design | Validate analytics and knowledge gap integration